## Visual
| Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
| January | February | March | April | May | June | July | August | September | October | November | December
Legislative communications | Track commission-related bills
Vote to support priority behavioral health bills
Legislators present bills to the Commission
Testify on bills
Meet with Legislative Policy Committee
Send report to Legislature
Meet with legislative leadership
[10 empty] | Meet with HHS & Executive Approp leadership | Meet with Legislative Policy Committee
Policy and budget recommendations |  |  | Update process for developing recommendations
Set timelines and expectations for committees
Committees develop recommendations
Committees present recommendations
Finalize recommendations
Strategic plan | Status report on tactics
Status report on tactics
Update data review as needed, including legislative audit findings
Solicit feedback on adjustments to strategic plan
Vote on any changes to strategic plan
Data dashboard | Design dashboards
Present to dashboards to Commission
Convene private sector |  |  |  |  | Prepare for private sector convening
Present data to private sector
Annual report | [7 empty] | Develop report
Vote on report

## 2026 policy areas
Prevention and Early Intervention
Key action steps | Responsible Unit | Due date | Status | Notes
Develop tactics to prevent suicide | Suicide Prevention Committee | 2026-01-15
Recommend priorities for preventing youth behavioral health challenges | Early Childhood Mental Health Working Group | 2026-04-16
Identify opportunities and barriers to the implementation of a private sector reimbursement model for first episode of psychosis coordinated specialty care | Treatment and Recovery Committee | 2026-08-20
Create a framework for school-based behavioral health services | School-Based Behavioral Health Subcommittee | 2026-09-17
Crisis
Key action steps | Responsible Unit | Due date | Status | Tactic
Develop tactics to expand crisis services as needed | Behavioral Health Crisis Response Committee | 2026-09-17
Identify models to improve sustainability of crisis services | Behavioral Health Crisis Response Committee | 2026-09-17
Evaluate the effectiveness of current crisis services | Behavioral Health Crisis Response Committee | 2026-09-17
Develop an electronic system to create and track temporary civil commitment sheets | Office of Substance Use and Mental Health | 2026-10-15
Treatment
Key action steps | Responsible Unit | Due date | Status | Tactic
Recommend statutory changes to the county mental health and substance use codes | Utah Behavioral Health Commission | 2026-07-16
Assess available data on access to medications for opioid use disorder | Treatment and Recovery Committee | 2026-08-20
Analyze options to monitor and improve the adequacy and accuracy of commercial health insurance networks | Office of Substance Use and Mental Health; Insurance Department | 2026-10-15
Status report on enhancing behavioral health infrastructure | Governor's workgroup | 2026-10-15
Develop tactics to improve coordination between the justice and behavioral health system | Forensic Behavioral Health Coordinating Council | 2026-10-15
Evaluate available data on behavioral health screenings, referrals, and follow-up in primary care | Office of Substance Use and Mental Health | 2026-10-15
Develop tactics to address behavioral health workforce needs | Health Workforce Advisory Council | 2026-11-19
Recommend needs for the integration of physical and behavioral health | One Utah Health Collaborative | 2026-11-19
Recovery
Key action steps | Responsible Unit | Due date | Status | Tactic
Identify method for assessing whether recovery support services are receiving adequate reimbursement | Office of Substance Use and Mental Health | 2026-10-15
Evaluate trends in stigma towards behavioral health | Office of Substance Use and Mental Health | 2026-10-15

## Master timeline
Items due in January
Key action steps | Start date | End date | Status | Notes
Legislators present bills to the Commission | 2026-01-15 | 2026-01-15
State Hospital presents Master Plan to Commission | 2026-01-15 | 2026-01-15
Status report on Suicide Prevention Committee tactics | 2026-01-15 | 2026-01-15
Staff circulate potential bills for e-vote on priority bills | 2026-01-29 | 2026-01-29
Items due in February
Key action steps | Start date | End date | Status | Tactic
Conduct e-vote on priority bills | 2026-02-05 | 2026-02-05
Staff circulate potential bills for vote on priority bills | 2026-02-11 | 2026-02-11
Testify in support of Commission recommendations to Social Services Appropriations | TBD | TBD
Conduct second vote on priority bills | 2026-02-18 | 2026-02-18
Items due in March
Key action steps | Start date | End date | Status | Tactic
Update process for developing and submitting recommendations | 2026-03-01 | 2026-03-31
Set timelines and expectations for committees | 2026-03-01 | 2026-03-31
Items due in April
Key action steps | Start date | End date | Status | Tactic
Status report on Early Childhood Mental Health Working Group tactics | 2026-04-16 | 2026-04-16
Present dashboards to the Commission | 2026-04-16 | 2026-04-16
Items due in May
Key action steps | Start date | End date | Status | Tactic
Committees develop recommendations | 2026-03-01 | 2026-05-31
Items due in June
Key action steps | Start date | End date | Status | Tactic
Meet with Legislative Policy Committee | TBD | TBD
Items due in July
Key action steps | Start date | End date | Status | Tactic
Committee present recommendations | 2026-06-01 | 2026-07-31
Private sector convening | TBD | TBD
Items due in August
Key action steps | Start date | End date | Status | Tactic
Finalize recommendations | 2026-08-20 | 2026-08-20
Status report on Treatment and Recovery Committee tactics: - First episode psychosis - Access to medications for opioid use disorder - Reimbursement for recovery services | 2026-08-20 | 2026-08-20
Status report on risk and protective factors for youth mental health (Prevention and Early Intervention Committee ) | 2026-08-20 | 2026-08-20
Items due in September
Key action steps | Start date | End date | Status | Tactic
Approve annual legislative report | 2026-09-17 | 2026-09-17
Status report on School-Based Behavioral Health Subcommittee tactics | 2026-09-17 | 2026-09-17
Status report on Behavioral Health Crisis Response Committee tactics - Expanding services as needed - Sustainability of services - Evaluating efficacy | 2026-09-17 | 2026-09-17
Send legislative report to Legislative Policy Committee and HHS Interim | 2026-09-30 | 2026-09-30
Items due in October
Key action steps | Start date | End date | Status | Tactic
Meet with legislative leadership | TBD | TBD
Meet with HHS & Executive Appropriations leadership | TBD | TBD
Status report on improving coordination between the justice and behavioral health systems (Forensic Behavioral Health Coordinating Council) | 2026-10-15 | 2026-10-15
Status report on Office of Substance Use and Mental Health tactics - Electronic civil commitment system - Commercial health insurance network adequacy - Behavioral health screenings/referrals/follow-ups in primary care - Recovery services reimbursement - Stigma analysis | 2026-10-15 | 2026-10-15
Status report on enhancing behavioral health infrastructure | 2026-10-15 | 2026-10-15
Update data in the strategic plan | 2026-09-01 | 2026-10-30
Items due in November
Key action steps | Start date | End date | Status | Tactic
Status report on addressing behavioral health workforce needs | 2026-11-19 | 2026-11-19
Status report on integration of physical and behavioral health from the One Utah Health Collaborative | 2026-11-19 | 2026-11-19
Meet with Legislative Policy Committee | TBD | TBD
Items due in December
Key action steps | Start date | End date | Status | Tactic
Vote to update strategic plan as needed | 2026-12-17 | 2026-12-17

## 2026 agenda structure
Workstream #1: Prevention and early intervention
Key action steps | Start date | End date | Status | Notes
Workstream #2: Crisis response
Key action steps | Start date | End date | Status | Tactic
Workstream #3: Treatment
Key action steps | Start date | End date | Status | Tactic
Workstream #4: Recovery
Key action steps | Start date | End date | Status | Tactic
Workstream #5: Data analysis
Key action steps | Start date | End date | Status | Tactic
Workstream #6: Legislative recommendations
Key action steps | Start date | End date | Status | Tactic
Placeholder for future workstreams
Key action steps | Start date | End date | Status | Tactic

## Strategic plan Prevention
Objective 1: Ensure all Utah children grow up with a strong foundation of good behavioral health
Tactic | Responsible Unit | Due date | Performance measures | Current status
1. Identify 1-2 tactics to address risk and protective factors for youth mental health. | Prevention and Early Intervention Committee Youth Behavioral Health Workgroup | Tactics due: July 31, 2026 | 31%: 9th - 12th graders reported three positive childhood experiences (2023). 25%: Youth need for mental health treatment (2023). 2.7%: Youth need for substance use disorder treatment (2023). 18%: Youth who seriously considered suicide in the past year (2023). | Currently creating the group
2. Request recommendations on priorities for preventing youth behavioral health challenges. | Early Childhood Mental Health Working Group | Recommendations due: December 31, 2025 | To be identified by the responsible unit. | Tactic development in progress
Objective 2: Expand coordination between education and behavioral health systems
1. Create a school-based mental health workgroup to develop a framework for school-based mental health services. | - Office of Substance Use and Mental Health - State Board of Education - Center for School-Based Health and Wellbeing Partnerships | Group due: December 31, 2025 Framework due: July 31, 2026 | To be identified by the responsible unit. | Pending creation of group
Objective 3: Expand early intervention models for behavioral health conditions
1. Collaborate with private sector stakeholders to identify opportunities and barriers to the implementation of a private sector reimbursement model for first episode of psychosis coordinated specialty care. | Treatment and Recovery Committee | 2026-07-01 | Overview of the current private sector approach to providing coordinated specialty care. Summary of implementation barriers for providing coordinated specialty care. Recommendations for next steps in expanding access to coordinated specialty care. Update data on clients based on findings: Number of Clinical High Risk of Psychosis individuals served: 55 (FY2024). Number of First Episode of Psychosis clients served: 42 (FY2024). Number of unserved First Episode Psychosis patients per year: 525 - 1,050 (FY2024). | Currently creating the group
2. Identify tactics for improving care coordination and transitions of care in behavioral health pediatric settings. | Treatment and Recovery Committee | 2027-07-01 | To be identified by responsible unit.
Objective 4: Support prevention and early intervention activities that reduce suicide deaths and attempts
To be developed by the responsible unit. | Suicide Prevention Committee and Coalition | 2025-12-31 | Rate of deaths due to suicide per 100,000 (2023): Males: 32. Females: 9. Adult serious suicidal ideation (2023): 7%. | They are working on their tactics

## Strategic plan Crisis
Objective 1: Expand crisis services to address identified need
Tactic | Responsible Unit | Current status | Performance measures | Notes
To be developed by the responsible unit. | Behavioral Health Crisis Response Committee | Tactics due: December 31, 2025 | To be developed by the responsible unit. | BHCRC will begin working on it this fall
Objective 2: Evaluate the sustainability of crisis services through private and public partnerships
1. Collaborate with the private sector to identify models that will improve the sustainability of crisis services. | Behavioral Health Crisis Response Committee | Update due: July 1, 2026 | Description of current funding of crisis services. Number of receiving centers and current funding sources. Number of MCOTs and current funding sources. 988 call center funding sources. | BHCRC will begin working on it this fall
Objective 3: Improve the effectiveness of crisis service
1. Evaluate the effectiveness of current crisis services in the public and private sector. | Office of Substance Use and Mental Health; Behavioral Health Crisis Response Committee | Update due: July 1, 2026 | The responsible unit will report data on the following items for 988 crisis centers, mobile crisis outreach teams, and receiving centers: Percentage of help-seekers who receive appropriate care. Patient satisfaction scores. Readmission rates. Symptom reduction. Successful linkage to continuing care within 7 days. Time to intervention: 988 call answer times Mobile dispatch times. Percentage of people seeking care who are turned away. | Stacy to talk to data group (WICHE) about how they are evaluating crisis services. Stacy will share learnings after the October meeting.
Objective 4: Improve alignment and coordination between emergency departments, crisis services, treatment services, and law enforcement
1. Develop an electronic system to create and track temporary civil commitment sheets. | Office of Substance Use and Mental Health | 2026-07-01 | To be developed by the responsible unit. | Already ongoing
2. Identify regions of Utah that need to improve alignment and coordination. | Behavioral Health Crisis Response Committee | 2027-07-01 | To be developed by the responsible unit. | Assigned to BHCRC
3. Explore barriers to implementing best practices in law enforcement crisis intervention training. | Behavioral Health Crisis Response Committee | 2028-07-01 | To be identified through Tactic 3: Percentage of law enforcement agencies that are implementing law enforcement crisis intervention training according to best practices. List of barriers to implementation. | Assigned to BHCRC

## Strategic plan Treatment
Objective 1: Improve alignment and coordination within and across the public and private behavioral health systems to reduce gaps in services
Tactic | Responsible Unit | Current status | Performance measures | Notes
1. Identify potential changes to the state's and counties' behavioral health responsibilities to be more patient-centered and ensure access. | Office of Substance Use and Mental Health | Update due: December 31, 2025 | To be developed by the responsible unit. | Commission will create workgroup
2. Collaborate with the Insurance Department to analyze options to monitor and improve the adequacy and accuracy of commercial health insurance networks. | Office of Substance Use and Mental Health; Insurance Department | Update due: July 1, 2026 | To be developed through collaboration with the Insurance Department. | We are waiting to see what Rep. Eliason's bill does. Potential idea = creating a complaint mechanism for behavioral health providers to submit evidence of issues with insurance companies.
3. Organize a convening with employers and private health insurance companies to understand the barriers the private sector faces in improving behavioral health care in Utah. | Utah Behavioral Health Commission | Update due: July 1, 2026 | Report that synthesizes the barriers that the private sector faces in improving behavioral health care. | Talk to Tammer about next steps
4. Review study funded by HB365 on mental health therapy wait times for children and develop tactics as necessary. | Office of Substance Use and Mental Health | 2027-12-31 | To be identified through study in Tactic 4: Wait times for pediatric mental health care appointments. Factors impacting wait times. | RFP has been released
5. Evaluate access to day treatment, intensive outpatient, and residential treatment services for individuals in the public and private sector. | Treatment and Recovery Committee | 2028-07-01 | Methodology for evaluating access to services. Estimate of unmet need for accessing services. | Waiting until Commission approves workgroups.
6. Request recommendations from the Governor’s workgroup to enhance behavioral health infrastructure. | Governor’s workgroup to enhance behavioral health infrastructure | 2026-07-01 | Number of inpatient behavioral health beds for patients with serious mental illness. Other metrics to be identified by responsible unit. | Have not yet contacted Dallas and Kyle about this group
Objective 2: Improve the quality of behavioral health treatment services
1. Develop a behavioral health dashboard that measures diagnosis, use of care, and cost of care across the public and private sector. | Office of Substance Use and Mental Health | 2026-07-01 | To be identified through Tactic 1. | In development
2. Assess available data on access to medications for opioid use disorder. | Office of Substance Use and Mental Health; Treatment and Recovery Committee | 2026-07-01 | To be identified through Tactic 1: Buprenorphine prescription rates by region. Methadone prescription rates by region. Naltrexone prescription rates by region. Other metrics identified by responsible unit. | Mia and Stacy to start researching evaluation approaches to methadone, buprenorphine, and naltrexone prescriptions.
3. Collaborate with the Insurance Department to identify tactics for improving parity of behavioral and physical health services. | Treatment and Recovery Committee; Insurance Department | 2027-07-01 | Recommendations for improving parity and increasing patient access to behavioral health providers, which may impact the rate of use of out-of-network behavioral health providers and increase reimbursement for behavioral health providers: - Behavioral health out-of-network use compared to medical/surgical for acute inpatient facility: 5.1x (2021). - All behavioral health clinicians out-of-network use compared to medical/surgical for office visits: 3.4x (2021). - Reimbursement for medical/surgical compared to behavioral health: 39.2% (2021). | 1. We will incorporate data on parity into our dashboard. 2. Discuss with the Treatment Committee when they begin, which Tanji is joining.
4. Identify barriers to expanding evidence-based treatment for substance use disorder, including stimulant use disorder. | Treatment and Recovery Committee | 2028-07-01 | Report that analyzes access to evidence-based stimulant use disorder treatment and describes barriers to expanding access, including the percentage of Utahns with stimulant use disorder receiving treatment. | Waiting until Commission approves workgroups.
Objective 3: Improve coordination between the justice and behavioral health system
To be developed by responsible unit. | Forensic Mental Health Coordinating Council | 2026-07-01 | To be identified by responsible unit. | Meeting scheduled with chairs to discuss for 8/29
Objective 4: Expand the behavioral health workforce to meet the community needs
To be developed by responsible unit. | Health Workforce Advisory Council | 2026-07-01 | To be identified by responsible unit. | Need to check in with Kendall on the status.
Objective 5: Expand integration of behavioral and physical health care
1. Evaluate available data on behavioral health screenings, referrals, and follow-up in primary care in the public and private sectors. | Office of Substance Use and Mental Health | 2026-07-01 | To be identified through Tactic 1: Behavioral health screening rates for adults in primary care settings. | Need to ask Patrice about data availability; don't have capacity right now
2. Request recommendations that align with Commission priorities on the integration of physical and behavioral health. | One Utah Health Collaborative | 2026-12-31 | To be identified by responsible unit. | Will discuss in next meeting with Collaborative
3. Identify barriers to expanding evidence-based approaches to integrated care. | Treatment and Recovery Committee | 2027-07-01 | To be identified by responsible unit, including recommendations on tactics to expand evidence-based approaches to integrated care. | Waiting until Commission approves workgroups.
4. Identify options for improving information sharing across physical and behavioral health providers. | Treatment and Recovery Committee | 2028-07-01 | To be identified by responsible unit. | Waiting until Commission approves workgroups.

## Strategic plan Recovery
Objective 1: Promote sustainable and appropriate funding for recovery support services
Tactic | Responsible Unit | Due date | Performance measures | Current status
1. Identify method for assessing whether recovery support services are receiving adequate reimbursement. | Office of Substance Use and Mental Health | 2026-07-01 | Method for assessing whether recovery support services are receiving adequate reimbursement. | Stacy checking if we have the list of recovery services. What research has already been done Interviews
2. Identify recovery services that are not receiving any and/or adequate reimbursement. | Office of Substance Use and Mental Health | 2026-12-31 | Summary of recovery services that are not receiving any or adequate reimbursement.
3. Analyze potential models for creating sustainable funding for these services. | Office of Substance Use and Mental Health | 2027-12-31 | Recommended model to create sustainable funding.
4. Explore options for expanding private health insurance reimbursement for peer support specialists. | Treatment and Recovery Committee | 2027-07-01 | Summary of opportunities and barriers for expanding private health insurance reimbursement, with recommendations for next steps. | Waiting until Commission approves workgroups.
Objective 2: Expand workplace and employment policies and practices that support people with mental health and substance use challenges
1. Collaborate with private employers to identify workplace policies and programs that support people in recovery or experiencing a behavioral health crisis. | Treatment and Recovery Committee | 2027-07-01 | Policy brief that identifies relevant workplace policies and programs and how they can be implemented. | Waiting until Commission approves workgroups.
2. Expand access to supported employment services to at least one additional site in the state. | Office of Substance Use and Mental Health | 2028-07-01 | Number of sites providing supported employment services. Percentage of individuals in Utah supported employment programs who receive competitive employment. | Will discuss with Sharon later
Objective 3: Evaluate trends in stigma towards mental health and substance use disorder
1. Explore opportunities for collecting Utah-level data that was previously collected by the National Survey on Drug Use and Health. | Office of Substance Use and Mental Health | 2026-07-01 | 18% of Utah youth who feel it is not okay to get mental health help (2023). 35% of Utah youth who have a high need for mental health treatment and who think it is not okay to get help (2023). 20% of Utah adults who needed mental health treatment and did not get help because they were worried about what other people would think (2022 - 2023). | Will check in October

## Statutory responsibilities
Clause | Duty | Status
(a) | establish a shared vision across public and private sectors for improving Utah's behavioral health systems; | Addressed by the strategic plan
(b) | make recommendations, including policy recommendations, and advise the governor, executive branch agencies, and the Legislature on matters pertaining to behavioral health; | Annual process established
(c) | provide feedback on proposed bills, rules, policies, and budgets relating to behavioral health; | Addressed through USAAV+
(d) | encourage participation in the commission's work by individuals and populations directly impacted by behavioral health issues, including family members of individuals with behavioral health issues; | Addressed through committee membership
(e) | engage private sector payers, providers, and business and employer groups in the commission's work; | In process; hope to address in part through data analysis
(f) | continually review and revise the master plan as appropriate; | Addressed through strategic plan
(g) | identify priorities and lead efforts to implement and advance those priorities by coordinating and collaborating closely with public and private persons throughout the state; | Addressed through strategic plan
(h) | identify areas where innovation is necessary to improve behavioral health access and care; | ?
(i) | cooperate with the Utah System of Higher Education, the State Board of Education, the Division of Professional Licensing, the Utah Health Workforce Advisory Council, and the department to oversee the creation and implementation of behavioral health workforce initiatives for the state; | Addressed through reporting structure with HWAC
(j) | collaborate with the Utah State Hospital, the Department of Corrections, county jails, and the department; | Partially addressed through Forensic Behavioral Health Coordinating Council
(k) | oversee coordination for the funding, implementation, and evaluation of suicide prevention efforts described in Section 26B-5-611; | Addressed through the Suicide Prevention Committee
(l) | develop methods or models for implementing and coherently communicating cross-sector strategies; | Addressed through strategic plan
(m) | hold the state's behavioral health systems accountable for clear, measurable outcomes; and | Only partially feasible (through data analysis)
(n) | maintain independence from the department and the governor such that the commission and its committees are able to provide independent advice and recommendations, especially regarding proposed bills and policy considerations. | Any concerns?